## Gantt Chart Template
| PROJECT TITLE | P2P Pet sitting Service |  |  |  |  | COMPANY NAME | [8 empty] | Animal Nest
| PROJECT MANAGER | Jinhan Han |  |  |  |  | DATE | [8 empty] | 08.09.2020
[5 empty] | September | [19 empty] | October | [19 empty] | November | [19 empty] | December | [19 empty] | January | [19 empty] | Feburuary | [19 empty] | March | [19 empty] | April | [19 empty] | May | [19 empty] | June | [19 empty] | July
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 9
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | UI.UX sample design for App and Web
1.1 | Front end design discussion | UI.UX designer, 2 Mobile App developer 1 react web developer | 2020-09-01 | 2020-09-02 | bar: WEEK 1 M to WEEK 1 T
1.1.1 | UI.UX sample design for App | UI.UX designer, 2 Mobile App developer | 2020-09-03 | 2020-09-17 | WEEK 1 W: UI.UX sample design for App
1.2 | UI.UX sample design for Web | UI.UX designer, 1 react web developer | 2020-09-21 | 2018-09-28 | WEEK 3 R: UI.UX sample design for Web
2 | Design for data table, algorithm & UML with research
2.1 | Discussion for datatable, algorithem & UML with research | 2 Mobile App developer 1 React web developer 2 Back end engineer 1 Project manager 1 Data marketing coordinator | 2020-09-01 | 2020-09-02 | bar: WEEK 1 M to WEEK 1 T
2.2 | Design for algorithm & UML | 2 Mobile App developer 1 React web developer 2 Back end engineer 1 Project manager | 2020-09-03 | 2020-09-28 | WEEK 1 W: Design for algorithm & UML
2.3 | Design for datatable | 2 Back end engineer | 2020-09-08 | 2020-09-28 | WEEK 2 M: Design for datable
2.4 | Risk Management | Malik M
3 | Front end design
3.1 | Android front end design | UI.UX designer, Android App developer |  |  | WEEK 5 M: Android front end design Android front end design Android front end design; WEEK 1 M: Android Internal function for calculation
3.2 | IOS front end design | UI.UX designer, IOS App developer |  |  | WEEK 5 M: IOS front end design IOS front end design IOS front end design; WEEK 1 M: IOS Internal function for calculation
3.3 | Web front end design | React web developer, UI.UX designer |  |  | WEEK 5 M: Web front end design Web front end design Web front end design; WEEK 1 M: Web internal function for calculation
4 | Developing back end system
4.1 | Developing back end design for transferring user data | Formal Back end engineer, 2 Mobile App developer |  |  | WEEK 5 M: Developing back end design for transferring user data Developing back end design for transferring user data
4.2 | Developing back end System for account information and transaction | Online transaction back end engineer, React web developer |  |  | WEEK 8 M: Developing back end System for account information and transaction
4.3 | Alpha version | 1 UI.UX designer 2 Mobile App developer 1 React web developer 2 Back end engineer 1 Project manager 1 Data marketing coordinator |  |  | WEEK 5 M: Finish up Alpha version Finish up Alpha version Finish up Alpha version
5 | Animal law service
3.3 | Planning consent for animal law | Law firm service |  |  | WEEK 5 M: Planning consent for animal law; WEEK 8 M: Planning consent for animal law
5 | Marketing strategies
5.1 | Planning marketing strategies | Project manager, Data Marketing Coordinator |  |  | WEEK 8 M: Marketing strategies
5.2 | Online Advertising |  |  |  | WEEK 5 M: Online Advertising; WEEK 5 T: Online Advertising; WEEK 9 M: Online Advertising
0 | Fixing or inspecting errors and bugs | All workers |  |  | WEEK 12 M: Fixing or inspecting errors and bugs Fixing or inspecting errors and bugs

## Try Smartsheet
Try Smartsheet for Free